## Overview
Goal | Make onboarding measurable, supported, and simple.
Primary Pain Points Solved | Access/submission issues; Support delays; Information overload
Key Deliverables | Start Here landing page; Automated reminders; Support triage & monitoring

## Timeline
Initiative | Owner | Start Week | End Week | Status | Progress | Notes
Start Here Landing Page | Ops Manager + Platform Engineer | 0 | 1 | ⚪ Planned | 0% | One-stop landing page, short videos
Orientation Micro-sessions | Curriculum Lead + TAs | 1 | 1 | ⚪ Planned | 0% | 3 x 20-min live sessions + recordings
Automated Checklist & Reminders | Product Ops | 1 | 2 | ⏳ In Progress | 40% | Email + push notifications
Support Triage Upgrade | Support Lead | 0 | 2 | ⏳ In Progress | 25% | Templates + SLA changes
Monitoring Dashboard | Analytics Engineer | 1 | 3 | ⚪ Planned | 0% | Error-rate alerts
Buddy Program | Student Success | 1 | 2 | ⚪ Planned | 0% | Pair students with buddies
Support QA & CSAT Loop | Support QA | 2 | 4 | ⚪ Planned | 0% | Post-ticket CSAT
Non-technical Track Material | Curriculum + Student Success | 3 | 6 | ⚪ Planned | 0% | Glossary + simple walkthroughs

## Roles
Role | Responsibility | Contact (example)
Ops Manager | Project owner, landing page, coordination | ops@xyz.com
Support Lead | Ticket SLA, templates, escalation | support@xyz.com
Analytics Engineer | Dashboard, data analysis | analytics@xyz.com
Platform Engineer | Link fixes, SSO stability | platform@xyz.com
Curriculum Lead / TAs | Live sessions, videos | curriculum@xyz.com
Student Success Manager | Buddy program, office hours | success@xyz.com
Support QA | Response quality & audits | qa@xyz.com

## Resources
Resource | Purpose | Priority
LMS + Submission Portal | Student learning & submissions | High
Ticketing System (Zendesk/Intercom) | Support tracking & triage | High
Email Automation (SendGrid/Mailchimp) | Reminders & checklist delivery | Moderate
Analytics tools (Mixpanel/GA) | Monitoring onboarding issues | High
Video Tools (YouTube) | Walkthrough clips for students | Moderate

## KPIs
Metric | Target | Current (sample)
Time to 1st Login | 90% within 48 hours | 85%
1st Assignment Submission | Median ≤ 72 hours | 78%
Missed Deadline Rate (A1) | Reduce by 70% | 25%
Support FCR | >80% | 72%
Support CSAT | ≥4/5 | 4.2 / 5

## Risks & Mitigations
Risk | Likelihood (High/Moderate/Low) | Impact (High/Moderate/Low) | Mitigation | Owner
Limited staff for sessions | Moderate | Moderate | Record sessions; use senior student volunteers | Student Success Manager
Broken platform links | Low | High | Ownership matrix; QA pre-orientation | Platform Engineer
Students ignore emails | Moderate | Moderate | Push notifications + SMS backup; concise emails | Product Ops